## Sheet1
SL no | Component | Component Code | Priority | Data | No of Tasks | Tasks | Start Date | End Date | Review | Final Draft | Tracking | Backlogs
1 | Landing Page | C1LP | P1 | Available | 4 | Brainstorm | 2024-12-15 | 2024-12-15 | 2024-12-16 | 2024-12-16
[6 empty] | Prepare Content Flow & Resource Gathering | 2024-12-16 | 2024-12-16 | 2024-12-17 | 2024-12-17
[6 empty] | Design | 2024-12-17 | 2024-12-17 | 2024-12-17 | 2024-12-17
[6 empty] | PPT Slide | 2024-12-17 | 2024-12-18 | 2024-12-18 | 2024-12-18
2 | Next Tech Portal | C2NTP | P3 | Available | 4 | Requirement Analysis | 2024-12-18 | 2024-12-18 | 2024-12-18 | 2024-12-18
[6 empty] | Create Content Specification | 2024-12-19 | 2024-12-19 | 2024-12-19 | 2024-12-19
[6 empty] | Design | 2024-12-20 | 2024-12-20 | 2024-12-20 | 2024-12-21
[6 empty] | PPT Slide | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-21
3 | CNC Module | C3CNCM | P2 | Not Available | 4 | Exisitng Resource Gathering | 2024-12-16 | TBD | TBD | TBD
[6 empty] | Module Design | TBD | TBD | TBD | TBD
[6 empty] | Design | TBD | TBD | TBD | TBD
[6 empty] | PPT Slide | TBD | TBD | TBD | TBD
4 | Basic E&E | C4BEE | P2 | Not Available | 4 | Exisitng Resource Gathering | 2024-12-16 | TBD | TBD | TBD
[6 empty] | Module Design | TBD | TBD | TBD | TBD
[6 empty] | Design | TBD | TBD | TBD | TBD
[6 empty] | PPT Slide | TBD | TBD | TBD | TBD
5 | Footwear & Apparel | C5FA | P2 | Not Available | 4 | Exisitng Resource Gathering | 2024-12-16 | TBD | TBD | TBD
[6 empty] | Module Design | TBD | TBD | TBD | TBD
[6 empty] | Design | TBD | TBD | TBD | TBD
[6 empty] | PPT Slide | TBD | TBD | TBD | TBD
6 | Welding | C6W | P2 | Not Available | 4 | Exisitng Resource Gathering | 2024-12-16 | TBD | TBD | TBD
[6 empty] | Module Design | TBD | TBD | TBD | TBD
[6 empty] | Design | TBD | TBD | TBD | TBD
[6 empty] | PPT Slide | TBD | TBD | TBD | TBD
7 | Registration Form | C7RF | P2 | Available | 4 | Design Reference | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-21
[6 empty] | Design | 2024-12-22 | 2024-12-22 | 2024-12-23 | 2024-12-23
[6 empty] | Functionality Design | 2024-12-24 | 2024-12-24 | 2024-12-25 | 2024-12-25
[6 empty] | PPT Slide | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-27
8 | Login Form | C8LF | P2 | Available | 4 | Design Reference | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-21
[6 empty] | Design | 2024-12-22 | 2024-12-22 | 2024-12-23 | 2024-12-23
[6 empty] | Functionality Design | 2024-12-24 | 2024-12-24 | 2024-12-25 | 2024-12-25
[6 empty] | PPT Slide | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-27

## Sheet2
Component | Deliverable | Tasks to Define | Dependencies | Notes | Priority
CNC |  | Identify content, design requirements, and functionality | None | Specify CNC content type
Basic Electrical and Electronics |  | Identify content, design requirements, and functionality | CNC | Specify training modules